## Project
		Project start:	Mon, 10/Feb/2020
						10/Feb/20					17/Feb/20					24/Feb/20
						10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	1
TASK	ASSIGNED TO	PROGRESS	START	END		M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
Phase 1: Analyze
Activity 1.1: Analyze the Project Reader	Konstantin, Kevin, Peter, Alexandra	100%	10/Feb/20	14/Feb/20
Activity 1.2: Brainstorming the problem	Konstantin, Kevin, Peter	85%	11/Feb/20	13/Feb/20
Activity 1.3: Client interview description	Konstantin, Peter, Alexandra	90%	13/Feb/20	18/Feb/20
Activity 1.4: Gantt Chart	Konstantin	100%	10/Feb/20	21/Feb/20
Activity 1.5: Project plan	Konstantin, Peter	100%	12/Feb/20	14/Feb/20
Phase 2: Designing
Activity 2.1: Writing the User requirement structures		10%	17/Feb/20	21/Feb/20
Activity 2.2: Creating relationships tables		1%	17/Feb/20	19/Feb/20
Activity 2.3: Prototyping of Web version		1%	19/Feb/20	21/Feb/20
Activity 2.4: Prototyping of Destop version		1%	18/Feb/20	21/Feb/20
Phase 3: Implementation
Activity 3.1: Split the work			02/Mar/20	03/Mar/20
Activity 3.2: Create a Desktop Widows Form project			02/Mar/20	03/Mar/20
Activity 3.3: Create classes Administrator and Manager			03/Mar/20	04/Mar/20
Activity 3.4: Create functionalities and instances			04/Mar/20	06/Mar/20
Activity 3.5: Create CRUD operations for employee			04/Mar/20	06/Mar/20
Activity 3.6: List of information for each employee			05/Mar/20	07/Mar/20
Activity 3.7: Information details for each Adm and Empls			04/Mar/20	06/Mar/20
Activity 3.8: Create a Web Application project			09/Mar/20	10/Mar/20
Activity 3.9: Basic interface for the visualization			09/Mar/20	11/Mar/20
Activity 3.10: Database Selection			10/Mar/20	12/Mar/20
Activity 3.11: Login system			11/Mar/20	13/Mar/20
Activity 3.12: Roles and connection with local DB			12/Mar/20	26/Mar/20
Activity 3.13: Fundamental UX design and form visualization			13/Mar/20	26/Mar/20
Activity 3.14: Fomrs and roles Listing			14/Mar/20	26/Mar/20
Activity 3.15: Department information			15/Mar/20	26/Mar/20
Activity 3.16: Shitfs implementation and visualization			16/Mar/20	26/Mar/20
Activity 3.17: Personal detail information Employee			17/Mar/20	26/Mar/20
Phase 4: Testing
Activity 4.1: Unit Tests for testing all the classes			01/Apr/20	14/Apr/20
Activity 4.2: Unit Test for testing all urls paths			02/Apr/20	15/Apr/20
Activity 4.2: Monkey testing with the Client			03/Apr/20	16/Apr/20
Activity 4.3: Fixing bugs session			04/Apr/20	17/Apr/20
Phase 5: Deployment
Activity 5.1: Deployment of the Web app version			20/Apr/20	23/Apr/20
Activity 5.2: Create an executable file for the Desktop app version			21/Apr/20	24/Apr/20